## Slide 1
Modernisation of Rail Route 2, Podgorica – Albanian Border: Feasibility Study and ESIA
WB20-MNE-TRA-02
Kickoff Meeting
19th May, 2020
Podgorica

## Slide 2: PROJECT DATA
Beneficiary Ministry of Transport and Maritime Affairs (MoTMA)
Railway Infrastructure of Montenegro (ŽICG)
Lender/ Lead IFI Kreditanstalt für Wiederaufbau (KfW)
Client European Commission, DG NEAR, represented by EIB
WBIF Grant Code WB20-MNE-TRA-02
Resources €1,300k – 27 Experts – 1,710 Expert-days
Start Date 19 May 2020
Duration 15 months

## Slide 3: STAKEHOLDERS
Ministry of Transport and Maritime Affairs (MoTMA)
Railway Infrastructure of Montenegro (ŽICG)
KfW as Lead IFI
EIB as IPF9 Contracting Authority (CA) and Client
European Commission, EU Delegation in Montenegro
Ministry of Finance - National IPA Coordinator (NIPAC)
Montenegrin Environmental Protection Agency (EPA)
Railway operation and maintenance companies
City and District authorities

## Slide 4: THE PROJECT
Railway line Podgorica – Albanian border (approx. 25 km):
is part of:
    the indicative extension of the TEN-T Core Corridor
    SEETO Route 2 Comprehensive Network [Podgorica (MNE) – Vlore (ALB)]
does not meet the minimum standards with respect to the TEN-T network regarding:
    Speed
    Electrification
    Length of loops
    Signalling

## Slide 5: THE PROJECT’S BACKGROUND
New Transport Development Strategy for the period 2019-2035 has been adopted from the Government of Montenegro: the modernization of the Podgorica – Albania border railway line is one of the main priorities
Tuzi station was declared a border station between Montenegro and Albania (June 2017)
Albanian railways are also developing their infrastructure in accordance with international standards

## Slide 6: PROJECT’S OBJECTIVES
Develop a Feasibility study for the modernisation of the Rail Route 2, including:
  a traffic study,
  options analysis,
  the conceptual design,
  a cost-benefit analysis and
  A full environmental and social impact assessment
Overall objective:
  making the railway a reliable and competitive mode of transport
  increase freight traffic
  serve passenger traffic and
  establish efficient cross border cooperation

## Slide 7: PROJECT PHASES
Inception Phase
Implementation Phase
Feasibility Study & ESIA
Traffic Study
Conceptual Design of preferred development scenario
Financial and Economic Analysis with CBA of the preferred development scenario
Environmental and Social Impact Assessment
Closing Phase
Finalization of Reports
Final Study Workshops
Mobilisation
Inception Report preparation
Development Scenario Analysis and selection of the preferred scenario
Preliminary Environmental and Social Management Plan preparation
Environmental and Social constraints assessment
Traffic Forecasts and Assignments
Identification and analysis of development scenario

## Slide 8: DESCRIPTION OF THE CONSULTANCY SERVICES
Inception Period
  Mobilization and internal Kick-Off Meeting
  Project Kick-Off Meeting
  Identification and approval of additional NKEs
  Collection and Review of previous studies, reports, records and other documents
  Thorough assessment of the existing situation
  Preparation of the Inception Report:
    The Inception Report is meant to illustrate the activities of this period and give a preview of the proposed management and execution of the project. It will include:
      A detailed Work Plan of activities
      Suggestions that would enhance and improve project’s performance
  Inception Meeting

## Slide 9: LIST OF DATA TO BE COLLECTED
Drawings – Engineering and technical data
  As build drawings for the existing track
Environmental and social data
  Planning documentation of Protected Areas / Emerald sites – Spatial Plans, Management Plans (if any)
Documents-Reports
Traffic Data
Information on related costs and revenues
  Any relevant historic costs (of designs, surveys etc) related to the proposed project
  Forecasted operation and maintenance costs
  Train purchase costs (if the purchase of new trains is required to operate the upgraded line)
  Tariff policy / unit revenues/ current total revenues (divided in passengers / freight)
  Freight traffic data
  Passenger traffic data
  Train traffic data
  Rail accidents
  Albanian Demand Model and reports / Status of the Albanian part of the railway line
  Description of the existing situation of the rail network in terms of lines, stations, interoperability issues, electrification, ERTMS, level crossings.
  Network statement
  The most recent railway development strategy
  The most recent update of the SPP
  Most recent (Municipal) Spatial Plan(s) and associated Strategic Environmental Assessment document(s)
  Structure of the rail sector in Montenegro (infrastructure managers, railway operators etc)
  Timetables and travel time on the rail network– also border crossing times and/or other bottlenecks
  Stations layouts
  As build drawings for existing structures e.g. bridges, tunnel
  Typical Cross sections

## Slide 10: DESCRIPTION OF THE CONSULTANCY SERVICES
Traffic Study
Collection and review the existing traffic data / transport model
Supplementary surveys and data collection
Gaps identification
Development of the Transport Demand Model
  Preparation of a Traffic Surveys Plan to be agreed with the Beneficiary prior to implementation
  The activities will be presented in the Traffic Model Report
  Inception
Notes: Having collected and reviewed the existing traffic data / transport model

## Slide 11: DESCRIPTION OF THE CONSULTANCY SERVICES
Identification of development scenarios
  Identification and description of specific development scenarios (rationale)
    “business-as-usual” development scenario,
    to limited rehabilitation,
    to full modernisation.
    “Abandoning the section is not an option.”
  For each development scenario:
    Traffic forecasts, assignments and impacts
    Assessment of the Environmental and Social constraints
    Indicative order of capital expenditure, operation and maintenance costs
  Preparation of the Alternative Development Scenarios Report (Interim report)
with and without:
new signalisation
electrification.

## Slide 12: DESCRIPTION OF THE CONSULTANCY SERVICES
Development Scenario Analysis and selection of the preferred scenario
  Comparative analysis of the different Development Scenarios based on:
    technical parameters
    financial-economic parameters
    environmental and social parameters
    other parameters (such as safety and accessibility)
  Proposal/selection of the preferred development scenario
  Preparation of the Development Scenario Analysis Report (Interim report)

## Slide 13: DESCRIPTION OF THE CONSULTANCY SERVICES
Conceptual Design of preferred development scenario
  Input:
    Baseline designs and other supporting documents
  Integration of environmental, spatial and resettlement aspects
  Elaboration of Masterplan for the stations
  Assessment of the requirements for rehabilitation of existing railway structures
  Preparation of the Conceptual Design along with its cost estimates
  Preparation of the Draft Conceptual Design Report (Interim report)

## Slide 14: Conceptual Design of preferred development scenario
 | General overview of the Line "Podgorica - Tuzi- Border with Albanian"
• | 25 km single track
• | Non electrified line
• | Currently used only for freight trains
• | Design speed 100km/h
 | Due to the poor condition speed 30km/h
 | Main Structures
• | Station Podgorica and Tuzi
• | Passing loop
• | 2 Level crossings
• | 3 Tunnels
• | 5 Bridges
• | 24 Culverts
DESCRIPTION OF THE CONSULTANCY SERVICES

## Slide 15: Conceptual Design of preferred development scenario
Activity 2.4 Conceptual design and Costs
Activity 2.3. preferred scenario
Geological Survey
Alignment
Structures
Track
Rehabilitation of existing structures
Road across the railway
New structure (if needed)
Stations
Platforms (TSI req.)
Layout Masterplan
Signalling and Telecommunication
Buildings
Electrification
Assessment
Hydrology
Input, baseline designs and supporting documents
DESCRIPTION OF THE CONSULTANCY SERVICES

## Slide 16: Conceptual Design of preferred development scenario
Rolling stock
Structural gauge
Alignment - operation
Stations, open line
Bridges, Tunnel
Electrification
Signalling
Level crossings interlocking
Civil engineering structures
Clearance, Pantograph
RAILWAY INTERFACES
DESCRIPTION OF THE CONSULTANCY SERVICES

## Slide 17: Conceptual Design of preferred development scenario
 | Main issues to be considered for the conceptual design
1 | Compliance to the TEN-T Standards
2 | Interoperability standards (wherever possible)
3 | Integrade Environmental aspects
4 | Integrade spatial and resettlements aspects
5 | Provision of the UIC-GB gauge
6 | Electrification with OCL
DESCRIPTION OF THE CONSULTANCY SERVICES
  Preparation of the Draft Conceptual Design Report (Interim report)

## Slide 18: DESCRIPTION OF THE CONSULTANCY SERVICES
Financial and Economic Analysis with CBA of the preferred Development Scenario
  Input:
    Cost estimates derived from the Conceptual Design activity
    Traffic assignments
    E&S assessment
  Financial analysis / Economic analysis
    In line with EU CBA guidelines
  Preparation of:
    the draft financial-economic model and
    the financial-economic model guidelines
  Preparation of the Draft Feasibility Study Report

## Slide 19: DESCRIPTION OF THE CONSULTANCY SERVICES
Environmental and Social Impact Assessment
  Review of background information, policy guidelines and relevant legislation
  Preparation of the Scoping Report and the detailed ESIA Work Plan
  Specific attention will be paid to issues related to:
    Physical environment
    Biological environment
    Social, economic and cultural environment
  Preparation of the draft ESIA package including;
    Draft Initial SEP, Draft P-ESMP, NTS
    Draft ESIA Report
    Draft LARPF
Notes: Stekeholders Engagement Plan, Preliminary E&S Management Plan, Non-Technical Summary
Draft Land Acquisition and Resettlement Policy Framework

## Slide 20: DESCRIPTION OF THE CONSULTANCY SERVICES
Project Close-out
  Final Study Workshop
  Preparation of the Final ESIA Report, including:
    Final P-ESMP
    Final LARPF
    Final SEP
    Final NTS
  Preparation of the Final Conceptual Design Report
  Preparation of the Final Financial Model
  Preparation of the Final Feasibility Report
  Preparation of the Project Executive Summary

## Slide 21: PROJECT TIMELINE
  * Interim reports / Technical Notes to be described and proposed in the Inception Report

## Slide 22: RISKS
Insufficient cooperation between the parties involved
  Early mobilisation
  Continuous collaboration
Lack and/or loss and/or decline of political will to promote the Project
  Efficient communication with the stakeholders involved
  Proper dissemination of the project’s purpose
Lengthy data collection period / Inconsistency of existing data / Lack or inadequacy of data
  Early review of data and early identification of missing data/information
  Continuous cooperation with MoTMA/ŽICG
  References in Montenegrin will be translated
Lack or delay on providing the existing transport model / inadequacy of data regarding the Albanian section
  Use of other existing transport models (REBIS, Podgorica bypass, AIC etc.)
  Adequate market research and/or traffic demand surveys for the estimation of potential demand from the Albanian side

## Slide 23: RISKS
Technical incompatibility of rail infrastructure in Montenegro and Albania
  Establishment of proper coordination with the respective stakeholders in Albania
Actions and comments / approvals are not provided in due time
  Continuous cooperation with the PIU
Some counterparts’ reluctance to work/communicate in English
  Ability of some team members to communicate in Montenegrin
Travel restrictions due to the pandemic banning the international experts from visiting Montenegro or limiting experts’ movements around the country
  Strengthening the team with local experts (to liaise with the local authorities and key stakeholders)
    Local Railway expert, already approved and mobilized
    Additional local experts identified – CVs to be submitted for approval asap
  Using technology (Skype, Zoom etc) to perform meetings
  Coordinating with client and beneficiary to adjust the workplan (if and where needed)

## Slide 24: LANGUAGE - COMMUNICATIONS
All formal communications will be in English.
Communications on technical issues with the local experts can be also made in Montenegrin.
Deliverables will be prepared in English and their final versions will be translated to Montenegrin. All other reports will be prepared in English.
Deliverables will be submitted to the PIU, KfW and EUD. The PIU shall ensure their distribution to other stakeholders.

## Slide 25: NEXT STEPS
Identification and approval of NKEs
Establishment of communication links
Collection of all related inputs (studies, regulatory requirements, local rulebooks and guidelines)
Review of previous studies and background information, thorough assessment of the current situation
Definition of the structure for the Feasibility Study and ESIA documentations
Site visit
Development of a detailed work plan (sub-activities, relationships, milestones, deliverables)
Preparation of the Inception Report